## Structura arborescenta
Nivel | Tip item | ID - Titlu | Status | Closure date | Estimare | Sprint
1 | User Story | 49879 - Chestionar: attach rules to questions, per-alias targets | New
1.1 | Task | 49907 - Attached-rules group on question modals, enforcement per row | New |  | 3
2 | User Story | 50102 - Chestionar: authoring comfort and safety nets | New
2.1 | Task | 49909 - Admin dialog check: v3 delta on top of 47457/47458 | New |  | 2
2.2 | Task | 49918 - Authoring guide for Business | New |  | 2
2.3 | Task | 49914 - Cart integration tests | New |  | 2
2.4 | Task | 49905 - Flow fields and answers snapshot | New |  | 3
2.5 | Task | 49910 - Graph validator | New |  | 3
2.6 | Task | 49888 - Help texts on questions and answers | New |  | 1
2.7 | Task | 49908 - Per-alias target mapping in the attached-rules row | New |  | 3
2.8 | Task | 49920 - Rule builder accepts placeholder values | New |  | 2
2.9 | Task | 49889 - Sections: metadata + Options grid column, sort and filter | New |  | 3
2.1 | Task | 49893 - validate() per condition; reinstate the at-least-one-effect check | New |  | 2
3 | User Story | 49882 - Chestionar: baseline configuration on Pachet centrala termica, DEV rollout, DoD demo | New
3.1 | Task | 49915 - Characteristic data completion in DEV | New |  | 1
3.2 | Task | 49917 - DEV rollout + DoD demonstration | New |  | 2
3.3 | Task | 49916 - Question lines and rules on the package | New |  | 2
4 | User Story | 49881 - Chestionar: cart enforcement of mandatory rule attachments | New
4.1 | Task | 49913 - Override validateProductOptions: mandatory violations, hidden required questions, snapshot | New |  | 5
4.2 | Task | 49912 - Spike: how the cart reaches the evaluator | Closed | 2026-08-31
5 | User Story | 49878 - Chestionar: configuration structure and evaluation endpoints | New
5.1 | Task | 49901 - ConfigurationEvaluationService (fixpoint) | New |  | 3
5.2 | Task | 49902 - Evaluate endpoint, DTOs, hydration, gateway routes | New |  | 3
5.3 | Task | 49904 - Integration tests through the browse flexpackage | New |  | 1
5.4 | Task | 49903 - OpenAPI spec + contract examples (wizard and form) | New |  | 2
5.5 | Task | 49906 - Structure endpoint with dependency graph | New
6 | User Story | 49884 - Chestionar: graph generality extensions (quantityFrom, context alias) | Closed | 2026-08-31
7 | User Story | 50103 - Chestionar: optional extensions | New
7.1 | Task | 49899 - Answer-level filtering: filterQuery on question lines | New |  | 4
7.2 | Task | 49921 - quantityFrom on the selection effect | New |  | 3
7.3 | Task | 49911 - Rule-side referential checks | New |  | 2
7.4 | Task | 49887 - Spike: option templates for reuse across packages, ordering UX | New |  | 2
8 | User Story | 49875 - Chestionar: questions and answers as Cart Input options | New
8.1 | Task | 49885 - Admin metadata: question and answer fields on the Cart Input modal | New |  | 3 | Sprint 17
8.2 | Task | 49886 - Read side: honour question and answer active flags, attributeName uniqueness validator | New |  | 4
9 | User Story | 49877 - Chestionar: rule effects - visibility, selection, set attributes, rule builder fields | New
9.1 | Task | 49895 - Effect fields + changeset + projection + validator | New |  | 2 | Sprint 17
9.2 | Task | 49897 - Effect resolution service (LineEffectResolver with contributions) | New |  | 3
9.3 | Task | 49922 - Implicit context alias in conditions | New |  | 2
9.4 | Task | 49900 - Questions as Rule Builder fields (answer dropdowns) | New |  | 3
9.5 | Task | 49898 - Admin rule form: conditions grid + effects group | New |  | 4
10 | User Story | 49876 - Chestionar: rule model v3 - answer conditions and compound conditions | New
10.1 | Task | 49891 - Attachment targets map + enforcement + validators | New |  | 3 | Sprint 17
10.2 | Task | 49890 - Entity + projection + changeset for rule conditions | New |  | 2
10.3 | Task | 49892 - Evaluator: SelectionContext, answer conditions, LineRef | New |  | 3 | Sprint 17
10.4 | Task | 49894 - Numeric-aware compare for ENUM characteristic values | New |  | 2 | Sprint 17
11 | User Story | 49880 - Chestionar: save-time consistency validators | Closed | 2026-08-31
12 | User Story | 49883 - Chestionar: value templating in filterQuery | New
12.1 | Task | 49919 - Placeholder substitution in filterQuery + validate() | New |  | 4
13 | User Story | 47460 - Rule versioning: Envers history + History section | New
13.1 | Task | 49491 - [UI] History section on the rule update view | New
13.2 | Task | 47461 - Envers recipe: @Audited entity + RevisionListener | New
13.3 | Task | 47463 - History endpoint on the rule CRUD controller | New
13.4 | Task | 47462 - Liquibase changesets for AUD + revision-info tables | New
Total estimare |  |  |  |  | 91

## Sumar status
Feature 49591 - [CPQ] Questionnaire & Rules Configurator
Indicator | Valoare | Observații | Status | Număr elemente
Total User Stories | 13 |  | Closed | 3
Total Tasks | 41 |  | New | 51
Total elemente | 54 | Stories și tasks
Items Closed | 3
Items New | 51
Progres finalizare | 5.556% | Closed / total elemente
Notă
Elementele fără status explicit în datele furnizate au fost marcate New.
Data de închidere pentru elementele indicate Closed a fost setată la 31.08.2026.